## Analysis
# | Issue | Root cause (one line) | Exact code change (one line) | Gaps to close before proceeding
3 | Amount doesn't refresh | The Amount calculation runs only in a jQuery .change() handler, which fires on blur only if the value changed. It does not fire on typing or paste, and the math is raw floating point. | In EquityMovement.aspx, replace the .change() handler with a recalcAmount() function bound to keyup change blur paste, rounded to 3 decimals; in GetXML4NewLoan, recompute NetAmount as Math.Round(units * price, 3) instead of trusting txtAmount.Text. | The 3-decimal rounding rule is unconfirmed with the business (check against the grid format). The exact "multiple clicks" sequence has not been reproduced, so one test on the user's browser (IE?) is needed.
4 | Workflow order (SaveAll > Next > Submit) | _ReportAction is empty on every postback, so GetRecords() sends RESET and the proc rebuilds the day's snapshot, wiping manual rows (on first load, Search, and SaveAll with no edited rows). Add and Delete rebind from the DB and lose unsaved grid edits, and Next doesn't save. | In GetRecords, use SqlCondition[6] = !string.IsNullOrEmpty(_ReportAction) ? _ReportAction : (Page.IsPostBack ? "SNAPSHOT" : "RESET"); add a SavePendingGridEdits() helper called from the Delete branch of grdEquityMovement_ItemCommand, case "SAVE" and case "NEXT"; in SaveRecords, skip ClearDetail() for bulk saves and suppress the duplicate confirmation alert. | The first-load RESET still wipes manual rows, so the proc needs a change to keep user-touched rows plus a transaction around the DELETE and INSERT. p_SaveEquityMovementReport has not been seen, so the ActionType values are unconfirmed. EquityMovementSummary.aspx(.cs) (Submit) has not been reviewed. The business must confirm the refresh-on-open behaviour. Root cause must be confirmed with a repro: add a manual row, click SaveAll with no edits, check whether it disappears.
5 | Screen takes minutes to load | The leading suspect is that RESET rebuilds the shared snapshot (p_GetEquityMovementReport, DELETE, INSERT DISTINCT) on open for the current business date, with concurrent users blocking each other. The whole DataTable is also held in ViewState just for the Excel export, and the grid has no paging. | Add Stopwatch logging around GetRecords() and GetBalanceReconStatus() in Page_Load; then load with SNAPSHOT plus an explicit Refresh button, and move vwEquityMovement from ViewState to Session. | No timings yet and no SNAPSHOT vs RESET comparison in SSMS. p_GetEquityMovementReport and the execution plans have not been seen, and an index on EquityMovementReportSnapshot(AsOfDate) is unverified. ViewState size and row counts are unknown, and there is no per-user timing to explain "worse for some users". Moving to Session needs a decision on multi-tab use and session timeout. Skipping refresh on load needs business sign-off.
6 | Blue fields not editable on Edit | The Edit branch of grdEquityMovement_ItemCommand explicitly disables the controls. Loan # is never populated, Recon is copied from itself (txtNewRemarks.Text = txtNewRemarks.Text), Acct# is read from a template cell's .Text (always empty), and the bulk edit XML sends only ID, dates and Remarks. | In the Edit branch, set Enabled = true on TOE, Acct#, both currencies, ISIN/CUSIP, Price, Units and Loan #; fix txtNewRemarks.Text = txtRemarks.Text; populate txtTxnRefNbr; read Acct# from lblAcctNbr; add Toe, CollCCYCode, CCYCode, AcctNbr, SecCode, FaceAmountChange, NewPrice, NetAmount and TxnRefNbr to GetXML4UpdateBulk's single-record branch; and run ValidateInputs for "E" as well as "N". | p_SaveEquityMovementReport has not been seen and must be extended for action E (derive SecID/SecDesc/SEDOL/AcctCode, apply sign by TOE, set ActionType='EDIT', reject on completed days). The sign convention of the New path is unconfirmed. Business rules on which fields may change after a recon are open. The snapshot refresh needs a stable source key once Loan # is editable.
Basis: static review of EquityMovement.aspx, EquityMovement.aspx.cs and p_EquityMovementReport; nothing here has been reproduced yet.

## Rollout
Item | Detail
Common testing | Regression-test Add, Edit, Delete, SaveAll, Next and Submit in different orders, on both the current business date and a past date.
Release 1 (page-side) | Issue 3 and the page-side part of Issue 4 (GetRecords default, SavePendingGridEdits, SaveRecords tweaks).
Release 2 (proc / data contract) | Issue 4 proc change (keep user-touched rows, transaction), Issue 5 (timings, SNAPSHOT-on-load, Refresh button, Session instead of ViewState) and Issue 6 (editable fields plus p_SaveEquityMovementReport changes).
Inputs still needed | p_SaveEquityMovementReport; p_GetEquityMovementReport and execution plans; EquityMovementSummary.aspx(.cs) if Submit behaves oddly; load timings (Page_Load Stopwatch logs, SNAPSHOT vs RESET in SSMS on a non-prod copy).